## Sheet1
Time Table for Tasks and Milestones
Task | Dates | [5 empty] | Personnel Responsible
| 2014-11-10 | 2014-11-24 | 2014-12-05 | 2014-12-08 | 2014-12-15 | 2014-12-17
Construct Welcome/Login page | <-------------REQUIRED---------------> | [5 empty] | Nicholas Roudebush
Construct Account View page | <-------------REQUIRED---------------> | [5 empty] | Michael Esry
Construct New Account page | <-------------REQUIRED---------------> | [5 empty] | Bill Kolega
Integrate 3 main pages |  |  |  | <------------REQUIRED----------------> |  |  | ALL ENGINEERS
ManageHost Server & Github | <---------------------------------------REQUIRED----------------------------------> | [5 empty] | Tyler Steiner
Generate Reports & Documentation | <-Report 1-> | <-Report2-> | <-----DOCUMENTATION and FINAL REPORT---> |  |  |  | Tyler Steiner